## Stories
CSM Group Information Technology - Asset Management
Story | Time (hours) | Risk (10 is highest) | % Complete
Settings Module | 8 | 4 | 0
Password Manager (company info) | 6 | 2 | 0
Inventories | 6 | 4 | 0
Asset Manager | 15 | 8 | 0
Helpdesk (ticketing system) | 12 | 8 | 0
Reports | 12 | 7 | 0
Dashboard | 6 | 6 | 0
Release 1 (R1) Totals: | 65 | 5.58 | 0

## Explainations
Story explainations
Story | Description
Settings Module | The user should be able to update rates and group/team names in bulk. The user should also have the ability to add/delete user accounts to/from the system. Asset types can also be managed here. Helpdesk categories can be managed here. Set user/group permissions for the system itself.
Password Manager | Securely store passwords for accounts used on day-to-day basis for the IT department members to easily access.
Inventories | Create a process for keeping track of projects, software, licensing, etc.
Asset Manager | Track computers and equipment with specified rates and assignees.
Helpdesk | Track user issues/requests within the organization. Used for reporting and better management of resolving issues.
Reports | Filter options that result in different reports based on information stored in the database in the asset manager, inventories, and helpdesk modules. This will be used for a better "billback" system than what is currently being done.
Dashboard | Give the user nice graphs to easily see, review, and resolve issues with the asset manager and helpdesk tickets.